## Projects
Project ID | Project Name | Location | Project Manager | Start Date | Planned End Date | Budget | Project Type | Status
PRJ001 | Chennai Metro Line 4 Substructure | Chennai (Porur-Poonamallee) | Rajesh Kumar | 2023-01-15 | 2024-12-31 | 1200000000 | Infrastructure | Delayed
PRJ002 | OMR Cyber Gateway Tower Phase 2 | Chennai (OMR-Sholinganallur) | Priya Raman | 2023-03-01 | 2024-11-30 | 850000000 | Commercial | In Progress
PRJ003 | Marina Coastal Promenade Expansion | Chennai (Marina Beach) | Suresh Natarajan | 2023-01-10 | 2024-04-30 | 350000000 | Infrastructure | Completed
PRJ004 | Guindy Green Tech Park | Chennai (Guindy Industrial Estate) | Ananya Iyer | 2023-04-01 | 2025-02-28 | 950000000 | Commercial | In Progress
PRJ005 | Velachery Commercial Mall & Multiplex | Chennai (Velachery) | Karthik Subramanian | 2023-02-15 | 2024-10-31 | 750000000 | Commercial | Delayed
PRJ006 | Tambaram Smart Residential Township | Chengalpattu (Tambaram West) | Divya Venkatesh | 2023-05-01 | 2025-06-30 | 600000000 | Residential | In Progress
PRJ007 | Sriperumbudur EV Manufacturing Plant | Kanchipuram (Sriperumbudur) | Arunachalam M. | 2023-02-01 | 2024-09-30 | 1100000000 | Industrial | Delayed
PRJ008 | Porur Grade Separator & Junction | Chennai (Porur) | Meera Krishnan | 2023-06-01 | 2025-03-31 | 450000000 | Infrastructure | In Progress
PRJ009 | ECR Seaside Luxury Enclave | Chennai (ECR-Kovalam) | Vigneshwaran S. | 2023-01-01 | 2024-03-31 | 400000000 | Residential | Completed
PRJ010 | Poonamallee Logistics & Freight Hub | Tiruvallur (Poonamallee) | Deepa Balaji | 2023-07-01 | 2025-05-31 | 500000000 | Industrial | In Progress

## Project_Cost
Project ID | Date | Planned Cost | Actual Cost
PRJ001 | 2023-01-01 | 50000000 | 51000000
PRJ001 | 2023-02-01 | 50000000 | 52500000
PRJ001 | 2023-03-01 | 50000000 | 54000000
PRJ001 | 2023-04-01 | 50000000 | 56000000
PRJ001 | 2023-05-01 | 50000000 | 57500000
PRJ001 | 2023-06-01 | 50000000 | 59000000
PRJ001 | 2023-07-01 | 50000000 | 57000000
PRJ001 | 2023-08-01 | 50000000 | 58000000
PRJ001 | 2023-09-01 | 50000000 | 57500000
PRJ001 | 2023-10-01 | 50000000 | 59000000
PRJ001 | 2023-11-01 | 50000000 | 60000000
PRJ001 | 2023-12-01 | 50000000 | 61000000
PRJ001 | 2024-01-01 | 50000000 | 59500000
PRJ001 | 2024-02-01 | 50000000 | 60500000
PRJ001 | 2024-03-01 | 50000000 | 61500000
PRJ001 | 2024-04-01 | 50000000 | 62500000
PRJ001 | 2024-05-01 | 50000000 | 61000000
PRJ001 | 2024-06-01 | 50000000 | 62000000
PRJ002 | 2023-03-01 | 42000000 | 42000000
PRJ002 | 2023-04-01 | 42000000 | 42420000
PRJ002 | 2023-05-01 | 42000000 | 42840000
PRJ002 | 2023-06-01 | 42000000 | 43260000
PRJ002 | 2023-07-01 | 42000000 | 42420000
PRJ002 | 2023-08-01 | 42000000 | 42840000
PRJ002 | 2023-09-01 | 42000000 | 43680000
PRJ002 | 2023-10-01 | 42000000 | 42840000
PRJ002 | 2023-11-01 | 42000000 | 43260000
PRJ002 | 2023-12-01 | 42000000 | 42420000
PRJ002 | 2024-01-01 | 42000000 | 42840000
PRJ002 | 2024-02-01 | 42000000 | 43260000
PRJ002 | 2024-03-01 | 42000000 | 42840000
PRJ002 | 2024-04-01 | 42000000 | 42420000
PRJ002 | 2024-05-01 | 42000000 | 42840000
PRJ002 | 2024-06-01 | 42000000 | 43260000
PRJ003 | 2023-01-01 | 21875000 | 21438000
PRJ003 | 2023-02-01 | 21875000 | 21000000
PRJ003 | 2023-03-01 | 21875000 | 20562000
PRJ003 | 2023-04-01 | 21875000 | 20781000
PRJ003 | 2023-05-01 | 21875000 | 20344000
PRJ003 | 2023-06-01 | 21875000 | 20562000
PRJ003 | 2023-07-01 | 21875000 | 20125000
PRJ003 | 2023-08-01 | 21875000 | 20781000
PRJ003 | 2023-09-01 | 21875000 | 20344000
PRJ003 | 2023-10-01 | 21875000 | 20125000
PRJ003 | 2023-11-01 | 21875000 | 20562000
PRJ003 | 2023-12-01 | 21875000 | 20344000
PRJ003 | 2024-01-01 | 21875000 | 20125000
PRJ003 | 2024-02-01 | 21875000 | 20562000
PRJ003 | 2024-03-01 | 21875000 | 20344000
PRJ003 | 2024-04-01 | 21875000 | 20125000
PRJ004 | 2023-04-01 | 41000000 | 41410000
PRJ004 | 2023-05-01 | 41000000 | 41000000
PRJ004 | 2023-06-01 | 41000000 | 41820000
PRJ004 | 2023-07-01 | 41000000 | 41410000
PRJ004 | 2023-08-01 | 41000000 | 42230000
PRJ004 | 2023-09-01 | 41000000 | 41820000
PRJ004 | 2023-10-01 | 41000000 | 41410000
PRJ004 | 2023-11-01 | 41000000 | 41820000
PRJ004 | 2023-12-01 | 41000000 | 41410000
PRJ004 | 2024-01-01 | 41000000 | 41820000
PRJ004 | 2024-02-01 | 41000000 | 41410000
PRJ004 | 2024-03-01 | 41000000 | 41820000
PRJ004 | 2024-04-01 | 41000000 | 41410000
PRJ004 | 2024-05-01 | 41000000 | 41820000
PRJ004 | 2024-06-01 | 41000000 | 41410000
PRJ005 | 2023-02-01 | 39000000 | 40950000
PRJ005 | 2023-03-01 | 39000000 | 42120000
PRJ005 | 2023-04-01 | 39000000 | 42900000
PRJ005 | 2023-05-01 | 39000000 | 43680000
PRJ005 | 2023-06-01 | 39000000 | 44850000
PRJ005 | 2023-07-01 | 39000000 | 44460000
PRJ005 | 2023-08-01 | 39000000 | 46020000
PRJ005 | 2023-09-01 | 39000000 | 46800000
PRJ005 | 2023-10-01 | 39000000 | 45240000
PRJ005 | 2023-11-01 | 39000000 | 46410000
PRJ005 | 2023-12-01 | 39000000 | 47190000
PRJ005 | 2024-01-01 | 39000000 | 47580000
PRJ005 | 2024-02-01 | 39000000 | 45630000
PRJ005 | 2024-03-01 | 39000000 | 44850000
PRJ005 | 2024-04-01 | 39000000 | 46020000
PRJ005 | 2024-05-01 | 39000000 | 46800000
PRJ005 | 2024-06-01 | 39000000 | 47580000
PRJ006 | 2023-05-01 | 23000000 | 23000000
PRJ006 | 2023-06-01 | 23000000 | 23230000
PRJ006 | 2023-07-01 | 23000000 | 23000000
PRJ006 | 2023-08-01 | 23000000 | 23460000
PRJ006 | 2023-09-01 | 23000000 | 23230000
PRJ006 | 2023-10-01 | 23000000 | 23000000
PRJ006 | 2023-11-01 | 23000000 | 23230000
PRJ006 | 2023-12-01 | 23000000 | 23460000
PRJ006 | 2024-01-01 | 23000000 | 23230000
PRJ006 | 2024-02-01 | 23000000 | 23000000
PRJ006 | 2024-03-01 | 23000000 | 23230000
PRJ006 | 2024-04-01 | 23000000 | 23460000
PRJ006 | 2024-05-01 | 23000000 | 23230000
PRJ006 | 2024-06-01 | 23000000 | 23230000
PRJ007 | 2023-02-01 | 55000000 | 57200000
PRJ007 | 2023-03-01 | 55000000 | 58300000
PRJ007 | 2023-04-01 | 55000000 | 59400000
PRJ007 | 2023-05-01 | 55000000 | 61050000
PRJ007 | 2023-06-01 | 55000000 | 62150000
PRJ007 | 2023-07-01 | 55000000 | 63250000
PRJ007 | 2023-08-01 | 55000000 | 61600000
PRJ007 | 2023-09-01 | 55000000 | 62700000
PRJ007 | 2023-10-01 | 55000000 | 63800000
PRJ007 | 2023-11-01 | 55000000 | 64900000
PRJ007 | 2023-12-01 | 55000000 | 64350000
PRJ007 | 2024-01-01 | 55000000 | 66000000
PRJ007 | 2024-02-01 | 55000000 | 65450000
PRJ007 | 2024-03-01 | 55000000 | 64900000
PRJ007 | 2024-04-01 | 55000000 | 66550000
PRJ007 | 2024-05-01 | 55000000 | 67100000
PRJ007 | 2024-06-01 | 55000000 | 66000000
PRJ008 | 2023-06-01 | 20000000 | 20400000
PRJ008 | 2023-07-01 | 20000000 | 20600000
PRJ008 | 2023-08-01 | 20000000 | 21000000
PRJ008 | 2023-09-01 | 20000000 | 20800000
PRJ008 | 2023-10-01 | 20000000 | 21200000
PRJ008 | 2023-11-01 | 20000000 | 21000000
PRJ008 | 2023-12-01 | 20000000 | 21400000
PRJ008 | 2024-01-01 | 20000000 | 20800000
PRJ008 | 2024-02-01 | 20000000 | 21000000
PRJ008 | 2024-03-01 | 20000000 | 21200000
PRJ008 | 2024-04-01 | 20000000 | 20800000
PRJ008 | 2024-05-01 | 20000000 | 21000000
PRJ008 | 2024-06-01 | 20000000 | 21200000
PRJ009 | 2023-01-01 | 26667000 | 25867000
PRJ009 | 2023-02-01 | 26667000 | 25333000
PRJ009 | 2023-03-01 | 26667000 | 25600000
PRJ009 | 2023-04-01 | 26667000 | 25067000
PRJ009 | 2023-05-01 | 26667000 | 25333000
PRJ009 | 2023-06-01 | 26667000 | 24800000
PRJ009 | 2023-07-01 | 26667000 | 25600000
PRJ009 | 2023-08-01 | 26667000 | 25067000
PRJ009 | 2023-09-01 | 26667000 | 25333000
PRJ009 | 2023-10-01 | 26667000 | 24800000
PRJ009 | 2023-11-01 | 26667000 | 25067000
PRJ009 | 2023-12-01 | 26667000 | 25333000
PRJ009 | 2024-01-01 | 26667000 | 25067000
PRJ009 | 2024-02-01 | 26667000 | 25600000
PRJ009 | 2024-03-01 | 26667000 | 25067000
PRJ010 | 2023-07-01 | 21500000 | 21500000
PRJ010 | 2023-08-01 | 21500000 | 21715000
PRJ010 | 2023-09-01 | 21500000 | 21930000
PRJ010 | 2023-10-01 | 21500000 | 21500000
PRJ010 | 2023-11-01 | 21500000 | 21715000
PRJ010 | 2023-12-01 | 21500000 | 21715000
PRJ010 | 2024-01-01 | 21500000 | 21930000
PRJ010 | 2024-02-01 | 21500000 | 21500000
PRJ010 | 2024-03-01 | 21500000 | 21715000
PRJ010 | 2024-04-01 | 21500000 | 21715000
PRJ010 | 2024-05-01 | 21500000 | 21500000
PRJ010 | 2024-06-01 | 21500000 | 21715000

## Project_Progress
Project ID | Date | Planned Progress % | Actual Progress %
PRJ001 | 2023-01-01 | 0.04 | 0.03
PRJ001 | 2023-02-01 | 0.08 | 0.06
PRJ001 | 2023-03-01 | 0.13 | 0.1
PRJ001 | 2023-04-01 | 0.18 | 0.14
PRJ001 | 2023-05-01 | 0.24 | 0.18
PRJ001 | 2023-06-01 | 0.3 | 0.23
PRJ001 | 2023-07-01 | 0.37 | 0.28
PRJ001 | 2023-08-01 | 0.44 | 0.34
PRJ001 | 2023-09-01 | 0.51 | 0.4
PRJ001 | 2023-10-01 | 0.58 | 0.46
PRJ001 | 2023-11-01 | 0.65 | 0.52
PRJ001 | 2023-12-01 | 0.72 | 0.58
PRJ001 | 2024-01-01 | 0.78 | 0.63
PRJ001 | 2024-02-01 | 0.84 | 0.68
PRJ001 | 2024-03-01 | 0.89 | 0.72
PRJ001 | 2024-04-01 | 0.93 | 0.76
PRJ001 | 2024-05-01 | 0.96 | 0.79
PRJ001 | 2024-06-01 | 0.98 | 0.82
PRJ002 | 2023-03-01 | 0.05 | 0.05
PRJ002 | 2023-04-01 | 0.1 | 0.09
PRJ002 | 2023-05-01 | 0.16 | 0.15
PRJ002 | 2023-06-01 | 0.22 | 0.21
PRJ002 | 2023-07-01 | 0.29 | 0.28
PRJ002 | 2023-08-01 | 0.36 | 0.35
PRJ002 | 2023-09-01 | 0.43 | 0.42
PRJ002 | 2023-10-01 | 0.5 | 0.49
PRJ002 | 2023-11-01 | 0.57 | 0.56
PRJ002 | 2023-12-01 | 0.64 | 0.62
PRJ002 | 2024-01-01 | 0.7 | 0.68
PRJ002 | 2024-02-01 | 0.76 | 0.74
PRJ002 | 2024-03-01 | 0.81 | 0.79
PRJ002 | 2024-04-01 | 0.86 | 0.84
PRJ002 | 2024-05-01 | 0.9 | 0.88
PRJ002 | 2024-06-01 | 0.93 | 0.91
PRJ003 | 2023-01-01 | 0.06 | 0.06
PRJ003 | 2023-02-01 | 0.12 | 0.13
PRJ003 | 2023-03-01 | 0.19 | 0.2
PRJ003 | 2023-04-01 | 0.26 | 0.27
PRJ003 | 2023-05-01 | 0.33 | 0.35
PRJ003 | 2023-06-01 | 0.4 | 0.42
PRJ003 | 2023-07-01 | 0.48 | 0.5
PRJ003 | 2023-08-01 | 0.56 | 0.58
PRJ003 | 2023-09-01 | 0.64 | 0.66
PRJ003 | 2023-10-01 | 0.72 | 0.74
PRJ003 | 2023-11-01 | 0.8 | 0.82
PRJ003 | 2023-12-01 | 0.87 | 0.89
PRJ003 | 2024-01-01 | 0.92 | 0.94
PRJ003 | 2024-02-01 | 0.96 | 0.97
PRJ003 | 2024-03-01 | 0.98 | 0.99
PRJ003 | 2024-04-01 | 1 | 1
PRJ004 | 2023-04-01 | 0.05 | 0.04
PRJ004 | 2023-05-01 | 0.1 | 0.09
PRJ004 | 2023-06-01 | 0.15 | 0.14
PRJ004 | 2023-07-01 | 0.21 | 0.2
PRJ004 | 2023-08-01 | 0.27 | 0.26
PRJ004 | 2023-09-01 | 0.33 | 0.32
PRJ004 | 2023-10-01 | 0.39 | 0.38
PRJ004 | 2023-11-01 | 0.45 | 0.44
PRJ004 | 2023-12-01 | 0.51 | 0.5
PRJ004 | 2024-01-01 | 0.57 | 0.56
PRJ004 | 2024-02-01 | 0.63 | 0.61
PRJ004 | 2024-03-01 | 0.68 | 0.66
PRJ004 | 2024-04-01 | 0.73 | 0.71
PRJ004 | 2024-05-01 | 0.77 | 0.75
PRJ004 | 2024-06-01 | 0.81 | 0.79
PRJ005 | 2023-02-01 | 0.05 | 0.04
PRJ005 | 2023-03-01 | 0.11 | 0.08
PRJ005 | 2023-04-01 | 0.17 | 0.12
PRJ005 | 2023-05-01 | 0.23 | 0.16
PRJ005 | 2023-06-01 | 0.3 | 0.2
PRJ005 | 2023-07-01 | 0.37 | 0.25
PRJ005 | 2023-08-01 | 0.44 | 0.3
PRJ005 | 2023-09-01 | 0.51 | 0.36
PRJ005 | 2023-10-01 | 0.58 | 0.42
PRJ005 | 2023-11-01 | 0.65 | 0.48
PRJ005 | 2023-12-01 | 0.72 | 0.54
PRJ005 | 2024-01-01 | 0.79 | 0.6
PRJ005 | 2024-02-01 | 0.85 | 0.65
PRJ005 | 2024-03-01 | 0.9 | 0.69
PRJ005 | 2024-04-01 | 0.94 | 0.73
PRJ005 | 2024-05-01 | 0.97 | 0.76
PRJ005 | 2024-06-01 | 0.99 | 0.79
PRJ006 | 2023-05-01 | 0.04 | 0.04
PRJ006 | 2023-06-01 | 0.08 | 0.08
PRJ006 | 2023-07-01 | 0.13 | 0.12
PRJ006 | 2023-08-01 | 0.18 | 0.17
PRJ006 | 2023-09-01 | 0.24 | 0.23
PRJ006 | 2023-10-01 | 0.3 | 0.29
PRJ006 | 2023-11-01 | 0.36 | 0.35
PRJ006 | 2023-12-01 | 0.42 | 0.41
PRJ006 | 2024-01-01 | 0.48 | 0.47
PRJ006 | 2024-02-01 | 0.54 | 0.53
PRJ006 | 2024-03-01 | 0.6 | 0.58
PRJ006 | 2024-04-01 | 0.65 | 0.63
PRJ006 | 2024-05-01 | 0.7 | 0.68
PRJ006 | 2024-06-01 | 0.74 | 0.72
PRJ007 | 2023-02-01 | 0.05 | 0.03
PRJ007 | 2023-03-01 | 0.1 | 0.07
PRJ007 | 2023-04-01 | 0.16 | 0.11
PRJ007 | 2023-05-01 | 0.23 | 0.16
PRJ007 | 2023-06-01 | 0.3 | 0.21
PRJ007 | 2023-07-01 | 0.37 | 0.27
PRJ007 | 2023-08-01 | 0.45 | 0.33
PRJ007 | 2023-09-01 | 0.53 | 0.4
PRJ007 | 2023-10-01 | 0.61 | 0.47
PRJ007 | 2023-11-01 | 0.69 | 0.54
PRJ007 | 2023-12-01 | 0.76 | 0.61
PRJ007 | 2024-01-01 | 0.83 | 0.67
PRJ007 | 2024-02-01 | 0.89 | 0.73
PRJ007 | 2024-03-01 | 0.94 | 0.78
PRJ007 | 2024-04-01 | 0.97 | 0.82
PRJ007 | 2024-05-01 | 0.99 | 0.85
PRJ007 | 2024-06-01 | 1 | 0.87
PRJ008 | 2023-06-01 | 0.04 | 0.03
PRJ008 | 2023-07-01 | 0.09 | 0.07
PRJ008 | 2023-08-01 | 0.15 | 0.12
PRJ008 | 2023-09-01 | 0.21 | 0.17
PRJ008 | 2023-10-01 | 0.28 | 0.23
PRJ008 | 2023-11-01 | 0.35 | 0.29
PRJ008 | 2023-12-01 | 0.42 | 0.35
PRJ008 | 2024-01-01 | 0.49 | 0.41
PRJ008 | 2024-02-01 | 0.56 | 0.47
PRJ008 | 2024-03-01 | 0.63 | 0.53
PRJ008 | 2024-04-01 | 0.69 | 0.59
PRJ008 | 2024-05-01 | 0.75 | 0.65
PRJ008 | 2024-06-01 | 0.8 | 0.7
PRJ009 | 2023-01-01 | 0.07 | 0.07
PRJ009 | 2023-02-01 | 0.14 | 0.14
PRJ009 | 2023-03-01 | 0.21 | 0.22
PRJ009 | 2023-04-01 | 0.29 | 0.3
PRJ009 | 2023-05-01 | 0.37 | 0.38
PRJ009 | 2023-06-01 | 0.45 | 0.47
PRJ009 | 2023-07-01 | 0.53 | 0.55
PRJ009 | 2023-08-01 | 0.62 | 0.64
PRJ009 | 2023-09-01 | 0.71 | 0.73
PRJ009 | 2023-10-01 | 0.79 | 0.81
PRJ009 | 2023-11-01 | 0.86 | 0.88
PRJ009 | 2023-12-01 | 0.92 | 0.94
PRJ009 | 2024-01-01 | 0.96 | 0.97
PRJ009 | 2024-02-01 | 0.98 | 0.99
PRJ009 | 2024-03-01 | 1 | 1
PRJ010 | 2023-07-01 | 0.05 | 0.05
PRJ010 | 2023-08-01 | 0.11 | 0.1
PRJ010 | 2023-09-01 | 0.17 | 0.16
PRJ010 | 2023-10-01 | 0.24 | 0.23
PRJ010 | 2023-11-01 | 0.31 | 0.3
PRJ010 | 2023-12-01 | 0.38 | 0.37
PRJ010 | 2024-01-01 | 0.46 | 0.44
PRJ010 | 2024-02-01 | 0.53 | 0.51
PRJ010 | 2024-03-01 | 0.6 | 0.58
PRJ010 | 2024-04-01 | 0.67 | 0.65
PRJ010 | 2024-05-01 | 0.73 | 0.71
PRJ010 | 2024-06-01 | 0.79 | 0.77

## Milestones
Milestone ID | Project ID | Milestone Name | Planned Date | Actual Date | Status
MLS001 | PRJ001 | Site Clearance & Soil Investigation | 2023-03-31 | 2023-04-10 | Completed
MLS002 | PRJ001 | Substructure & Foundation Piling | 2023-08-31 | 2023-09-20 | Completed
MLS003 | PRJ001 | RCC Superstructure & Pier Casting | 2024-02-28 | 2024-05-15 | Completed
MLS004 | PRJ001 | Viaduct Erection & Track Bed | 2024-05-31 |  | Delayed
MLS005 | PRJ001 | Signaling, Traction & Trial Runs | 2024-11-30 |  | In Progress
MLS006 | PRJ002 | Site Clearance & Excavation | 2023-04-30 | 2023-04-25 | Completed
MLS007 | PRJ002 | Basement Retaining Wall & Raft | 2023-08-31 | 2023-08-30 | Completed
MLS008 | PRJ002 | Tower Core & Superstructure (L1-L15) | 2024-01-31 | 2024-02-05 | Completed
MLS009 | PRJ002 | Glass Curtain Glazing & Facade | 2024-06-30 |  | In Progress
MLS010 | PRJ002 | High-Speed Elevators & Commissioning | 2024-10-31 |  | In Progress
MLS011 | PRJ003 | Coastal Survey & Environmental Clearance | 2023-02-28 | 2023-02-20 | Completed
MLS012 | PRJ003 | Seawall Reinforcement & Earthwork | 2023-06-30 | 2023-06-25 | Completed
MLS013 | PRJ003 | Paved Promenade & Cycling Tracks | 2023-11-30 | 2023-11-20 | Completed
MLS014 | PRJ003 | Solar Illumination & Public Amenities | 2024-02-28 | 2024-02-22 | Completed
MLS015 | PRJ003 | Landscaping & Public Opening Handover | 2024-04-30 | 2024-04-18 | Completed
MLS016 | PRJ004 | Geotechnical Survey & Demolition | 2023-05-31 | 2023-05-28 | Completed
MLS017 | PRJ004 | Deep Foundation & Diaphragm Wall | 2023-09-30 | 2023-10-05 | Completed
MLS018 | PRJ004 | Pre-cast Concrete Framing (G+8) | 2024-03-31 | 2024-04-02 | Completed
MLS019 | PRJ004 | IGBC Platinum HVAC & Solar Grid | 2024-08-31 |  | In Progress
MLS020 | PRJ004 | Interior Fitouts & Smart Building BMS | 2025-01-31 |  | In Progress
MLS021 | PRJ005 | Excavation & Water Table Dewatering | 2023-04-15 | 2023-05-10 | Completed
MLS022 | PRJ005 | Multi-Level Basement Parking Slab | 2023-09-15 | 2023-10-30 | Completed
MLS023 | PRJ005 | Anchor Store & Atrium Framing | 2024-01-31 | 2024-04-20 | Completed
MLS024 | PRJ005 | Multiplex Acoustic Shell & Escalators | 2024-05-31 |  | Delayed
MLS025 | PRJ005 | Retail Fitouts & Fire Safety NOC | 2024-09-30 |  | In Progress
MLS026 | PRJ006 | Master Plan Approval & Boundary Walls | 2023-06-30 | 2023-06-20 | Completed
MLS027 | PRJ006 | Towers A & B Substructure Piling | 2023-11-30 | 2023-12-05 | Completed
MLS028 | PRJ006 | Monolithic Mivan Shuttering (Floor 1-10) | 2024-04-30 | 2024-05-12 | Completed
MLS029 | PRJ006 | Plumbing, Electrical Conduits & Flooring | 2024-10-31 |  | In Progress
MLS030 | PRJ006 | Clubhouse, Sewage Plant & Handover | 2025-05-31 |  | In Progress
MLS031 | PRJ007 | Industrial Land Leveling & Grading | 2023-03-31 | 2023-03-25 | Completed
MLS032 | PRJ007 | Heavy Industrial Flooring & PEB Erection | 2023-07-31 | 2023-09-10 | Completed
MLS033 | PRJ007 | Battery Pack Assembly Cleanrooms | 2023-12-31 | 2024-03-15 | Completed
MLS034 | PRJ007 | Automated Conveyor & Robotic Cells | 2024-04-30 |  | Delayed
MLS035 | PRJ007 | High-Tension Substation & Trial Run | 2024-08-31 |  | Delayed
MLS036 | PRJ008 | Utility Diversion & Traffic Rerouting | 2023-07-31 | 2023-08-20 | Completed
MLS037 | PRJ008 | Pile Foundations & Pier Caps (P1-P24) | 2023-12-31 | 2024-01-25 | Completed
MLS038 | PRJ008 | Pre-stressed Concrete Girder Launching | 2024-05-31 | 2024-06-18 | Completed
MLS039 | PRJ008 | Deck Slab Casting & Bituminous Wearing | 2024-10-31 |  | In Progress
MLS040 | PRJ008 | Crash Barriers, Streetlights & Signage | 2025-02-28 |  | In Progress
MLS041 | PRJ009 | CRZ Regulatory Clearances & Boundary | 2023-02-15 | 2023-02-10 | Completed
MLS042 | PRJ009 | 24 Luxury Villa Foundation & Plinth | 2023-06-30 | 2023-06-25 | Completed
MLS043 | PRJ009 | Villa Superstructure & Terraces | 2023-10-31 | 2023-10-28 | Completed
MLS044 | PRJ009 | Italian Marble, Smart Automation & MEP | 2024-01-31 | 2024-01-20 | Completed
MLS045 | PRJ009 | Private Pools, Landscaping & Key Handover | 2024-03-31 | 2024-03-25 | Completed
MLS046 | PRJ010 | Topographical Survey & Industrial Approvals | 2023-08-31 | 2023-08-25 | Completed
MLS047 | PRJ010 | Laser Screed Heavy-Duty Flooring | 2023-12-31 | 2024-01-10 | Completed
MLS048 | PRJ010 | Pre-Engineered Steel Shed Erection | 2024-04-30 | 2024-05-08 | Completed
MLS049 | PRJ010 | Dock Levelers & Automated Fire Hydrants | 2024-10-31 |  | In Progress
MLS050 | PRJ010 | Solar Rooftop (1 MW) & Logistics Handover | 2025-04-30 |  | In Progress