## Raw_Projects
prj_id | Project_Name | Site_Location | Assigned_PM | Date_Commenced | Target_Completion | Approved_Budget_INR | Sector | Execution_Status
PRJ001 | Chennai Metro Line 4 Substructure | Chennai (Porur-Poonamallee) | Rajesh Kumar | 15/01/2023 | 31/12/2024 | INR 1,200,000,000 | Infrastructure | DELAYED
PRJ002 | OMR Cyber Gateway Tower Phase 2 | Chennai (OMR-Sholinganallur) | Priya Raman | 01/03/2023 | 30/11/2024 | INR 850,000,000 | Commercial | IN PROGRESS
PRJ003 | Marina Coastal Promenade Expansion | Chennai (Marina Beach) | Suresh Natarajan | 10/01/2023 | 30/04/2024 | INR 350,000,000 | Infrastructure | COMPLETED
PRJ004 | Guindy Green Tech Park | Chennai (Guindy Industrial Estate) | Ananya Iyer | 01/04/2023 | 28/02/2025 | INR 950,000,000 | Commercial | IN PROGRESS
PRJ005 | Velachery Commercial Mall & Multiplex | Chennai (Velachery) | Karthik Subramanian | 15/02/2023 | 31/10/2024 | INR 750,000,000 | Commercial | DELAYED
PRJ006 | Tambaram Smart Residential Township | Chengalpattu (Tambaram West) | Divya Venkatesh | 01/05/2023 | 30/06/2025 | INR 600,000,000 | Residential | IN PROGRESS
PRJ007 | Sriperumbudur EV Manufacturing Plant | Kanchipuram (Sriperumbudur) | Arunachalam M. | 01/02/2023 | 30/09/2024 | INR 1,100,000,000 | Industrial | DELAYED
PRJ008 | Porur Grade Separator & Junction | Chennai (Porur) | Meera Krishnan | 01/06/2023 | 31/03/2025 | INR 450,000,000 | Infrastructure | IN PROGRESS
PRJ009 | ECR Seaside Luxury Enclave | Chennai (ECR-Kovalam) | Vigneshwaran S. | 01/01/2023 | 31/03/2024 | INR 400,000,000 | Residential | COMPLETED
PRJ010 | Poonamallee Logistics & Freight Hub | Tiruvallur (Poonamallee) | Deepa Balaji | 01/07/2023 | 31/05/2025 | INR 500,000,000 | Industrial | IN PROGRESS

## Raw_Project_Cost
PRJ_CODE | Reporting_Month | PLANNED_EXP_INR | ACTUAL_EXP_INR
PRJ001 | 01-01-2023 | INR 50,000,000 | INR 51,000,000
PRJ001 | 01-02-2023 | INR 50,000,000 | INR 52,500,000
PRJ001 | 01-03-2023 | INR 50,000,000 | INR 54,000,000
PRJ001 | 01-04-2023 | INR 50,000,000 | INR 56,000,000
PRJ001 | 01-05-2023 | INR 50,000,000 | INR 57,500,000
PRJ001 | 01-06-2023 | INR 50,000,000 | INR 59,000,000
PRJ001 | 01-07-2023 | INR 50,000,000 | INR 57,000,000
PRJ001 | 01-08-2023 | INR 50,000,000 | INR 58,000,000
PRJ001 | 01-09-2023 | INR 50,000,000 | INR 57,500,000
PRJ001 | 01-10-2023 | INR 50,000,000 | INR 59,000,000
PRJ001 | 01-11-2023 | INR 50,000,000 | INR 60,000,000
PRJ001 | 01-12-2023 | INR 50,000,000 | INR 61,000,000
PRJ001 | 01-01-2024 | INR 50,000,000 | INR 59,500,000
PRJ001 | 01-02-2024 | INR 50,000,000 | INR 60,500,000
PRJ001 | 01-03-2024 | INR 50,000,000 | INR 61,500,000
PRJ001 | 01-04-2024 | INR 50,000,000 | INR 62,500,000
PRJ001 | 01-05-2024 | INR 50,000,000 | INR 61,000,000
PRJ001 | 01-06-2024 | INR 50,000,000 | INR 62,000,000
PRJ002 | 01-03-2023 | INR 42,000,000 | INR 42,000,000
PRJ002 | 01-04-2023 | INR 42,000,000 | INR 42,420,000
PRJ002 | 01-05-2023 | INR 42,000,000 | INR 42,840,000
PRJ002 | 01-06-2023 | INR 42,000,000 | INR 43,260,000
PRJ002 | 01-07-2023 | INR 42,000,000 | INR 42,420,000
PRJ002 | 01-08-2023 | INR 42,000,000 | INR 42,840,000
PRJ002 | 01-09-2023 | INR 42,000,000 | INR 43,680,000
PRJ002 | 01-10-2023 | INR 42,000,000 | INR 42,840,000
PRJ002 | 01-11-2023 | INR 42,000,000 | INR 43,260,000
PRJ002 | 01-12-2023 | INR 42,000,000 | INR 42,420,000
PRJ002 | 01-01-2024 | INR 42,000,000 | INR 42,840,000
PRJ002 | 01-02-2024 | INR 42,000,000 | INR 43,260,000
PRJ002 | 01-03-2024 | INR 42,000,000 | INR 42,840,000
PRJ002 | 01-04-2024 | INR 42,000,000 | INR 42,420,000
PRJ002 | 01-05-2024 | INR 42,000,000 | INR 42,840,000
PRJ002 | 01-06-2024 | INR 42,000,000 | INR 43,260,000
PRJ003 | 01-01-2023 | INR 21,875,000 | INR 21,438,000
PRJ003 | 01-02-2023 | INR 21,875,000 | INR 21,000,000
PRJ003 | 01-03-2023 | INR 21,875,000 | INR 20,562,000
PRJ003 | 01-04-2023 | INR 21,875,000 | INR 20,781,000
PRJ003 | 01-05-2023 | INR 21,875,000 | INR 20,344,000
PRJ003 | 01-06-2023 | INR 21,875,000 | INR 20,562,000
PRJ003 | 01-07-2023 | INR 21,875,000 | INR 20,125,000
PRJ003 | 01-08-2023 | INR 21,875,000 | INR 20,781,000
PRJ003 | 01-09-2023 | INR 21,875,000 | INR 20,344,000
PRJ003 | 01-10-2023 | INR 21,875,000 | INR 20,125,000
PRJ003 | 01-11-2023 | INR 21,875,000 | INR 20,562,000
PRJ003 | 01-12-2023 | INR 21,875,000 | INR 20,344,000
PRJ003 | 01-01-2024 | INR 21,875,000 | INR 20,125,000
PRJ003 | 01-02-2024 | INR 21,875,000 | INR 20,562,000
PRJ003 | 01-03-2024 | INR 21,875,000 | INR 20,344,000
PRJ003 | 01-04-2024 | INR 21,875,000 | INR 20,125,000
PRJ004 | 01-04-2023 | INR 41,000,000 | INR 41,410,000
PRJ004 | 01-05-2023 | INR 41,000,000 | INR 41,000,000
PRJ004 | 01-06-2023 | INR 41,000,000 | INR 41,820,000
PRJ004 | 01-07-2023 | INR 41,000,000 | INR 41,410,000
PRJ004 | 01-08-2023 | INR 41,000,000 | INR 42,230,000
PRJ004 | 01-09-2023 | INR 41,000,000 | INR 41,820,000
PRJ004 | 01-10-2023 | INR 41,000,000 | INR 41,410,000
PRJ004 | 01-11-2023 | INR 41,000,000 | INR 41,820,000
PRJ004 | 01-12-2023 | INR 41,000,000 | INR 41,410,000
PRJ004 | 01-01-2024 | INR 41,000,000 | INR 41,820,000
PRJ004 | 01-02-2024 | INR 41,000,000 | INR 41,410,000
PRJ004 | 01-03-2024 | INR 41,000,000 | INR 41,820,000
PRJ004 | 01-04-2024 | INR 41,000,000 | INR 41,410,000
PRJ004 | 01-05-2024 | INR 41,000,000 | INR 41,820,000
PRJ004 | 01-06-2024 | INR 41,000,000 | INR 41,410,000
PRJ005 | 01-02-2023 | INR 39,000,000 | INR 40,950,000
PRJ005 | 01-03-2023 | INR 39,000,000 | INR 42,120,000
PRJ005 | 01-04-2023 | INR 39,000,000 | INR 42,900,000
PRJ005 | 01-05-2023 | INR 39,000,000 | INR 43,680,000
PRJ005 | 01-06-2023 | INR 39,000,000 | INR 44,850,000
PRJ005 | 01-07-2023 | INR 39,000,000 | INR 44,460,000
PRJ005 | 01-08-2023 | INR 39,000,000 | INR 46,020,000
PRJ005 | 01-09-2023 | INR 39,000,000 | INR 46,800,000
PRJ005 | 01-10-2023 | INR 39,000,000 | INR 45,240,000
PRJ005 | 01-11-2023 | INR 39,000,000 | INR 46,410,000
PRJ005 | 01-12-2023 | INR 39,000,000 | INR 47,190,000
PRJ005 | 01-01-2024 | INR 39,000,000 | INR 47,580,000
PRJ005 | 01-02-2024 | INR 39,000,000 | INR 45,630,000
PRJ005 | 01-03-2024 | INR 39,000,000 | INR 44,850,000
PRJ005 | 01-04-2024 | INR 39,000,000 | INR 46,020,000
PRJ005 | 01-05-2024 | INR 39,000,000 | INR 46,800,000
PRJ005 | 01-06-2024 | INR 39,000,000 | INR 47,580,000
PRJ006 | 01-05-2023 | INR 23,000,000 | INR 23,000,000
PRJ006 | 01-06-2023 | INR 23,000,000 | INR 23,230,000
PRJ006 | 01-07-2023 | INR 23,000,000 | INR 23,000,000
PRJ006 | 01-08-2023 | INR 23,000,000 | INR 23,460,000
PRJ006 | 01-09-2023 | INR 23,000,000 | INR 23,230,000
PRJ006 | 01-10-2023 | INR 23,000,000 | INR 23,000,000
PRJ006 | 01-11-2023 | INR 23,000,000 | INR 23,230,000
PRJ006 | 01-12-2023 | INR 23,000,000 | INR 23,460,000
PRJ006 | 01-01-2024 | INR 23,000,000 | INR 23,230,000
PRJ006 | 01-02-2024 | INR 23,000,000 | INR 23,000,000
PRJ006 | 01-03-2024 | INR 23,000,000 | INR 23,230,000
PRJ006 | 01-04-2024 | INR 23,000,000 | INR 23,460,000
PRJ006 | 01-05-2024 | INR 23,000,000 | INR 23,230,000
PRJ006 | 01-06-2024 | INR 23,000,000 | INR 23,230,000
PRJ007 | 01-02-2023 | INR 55,000,000 | INR 57,200,000
PRJ007 | 01-03-2023 | INR 55,000,000 | INR 58,300,000
PRJ007 | 01-04-2023 | INR 55,000,000 | INR 59,400,000
PRJ007 | 01-05-2023 | INR 55,000,000 | INR 61,050,000
PRJ007 | 01-06-2023 | INR 55,000,000 | INR 62,150,000
PRJ007 | 01-07-2023 | INR 55,000,000 | INR 63,250,000
PRJ007 | 01-08-2023 | INR 55,000,000 | INR 61,600,000
PRJ007 | 01-09-2023 | INR 55,000,000 | INR 62,700,000
PRJ007 | 01-10-2023 | INR 55,000,000 | INR 63,800,000
PRJ007 | 01-11-2023 | INR 55,000,000 | INR 64,900,000
PRJ007 | 01-12-2023 | INR 55,000,000 | INR 64,350,000
PRJ007 | 01-01-2024 | INR 55,000,000 | INR 66,000,000
PRJ007 | 01-02-2024 | INR 55,000,000 | INR 65,450,000
PRJ007 | 01-03-2024 | INR 55,000,000 | INR 64,900,000
PRJ007 | 01-04-2024 | INR 55,000,000 | INR 66,550,000
PRJ007 | 01-05-2024 | INR 55,000,000 | INR 67,100,000
PRJ007 | 01-06-2024 | INR 55,000,000 | INR 66,000,000
PRJ008 | 01-06-2023 | INR 20,000,000 | INR 20,400,000
PRJ008 | 01-07-2023 | INR 20,000,000 | INR 20,600,000
PRJ008 | 01-08-2023 | INR 20,000,000 | INR 21,000,000
PRJ008 | 01-09-2023 | INR 20,000,000 | INR 20,800,000
PRJ008 | 01-10-2023 | INR 20,000,000 | INR 21,200,000
PRJ008 | 01-11-2023 | INR 20,000,000 | INR 21,000,000
PRJ008 | 01-12-2023 | INR 20,000,000 | INR 21,400,000
PRJ008 | 01-01-2024 | INR 20,000,000 | INR 20,800,000
PRJ008 | 01-02-2024 | INR 20,000,000 | INR 21,000,000
PRJ008 | 01-03-2024 | INR 20,000,000 | INR 21,200,000
PRJ008 | 01-04-2024 | INR 20,000,000 | INR 20,800,000
PRJ008 | 01-05-2024 | INR 20,000,000 | INR 21,000,000
PRJ008 | 01-06-2024 | INR 20,000,000 | INR 21,200,000
PRJ009 | 01-01-2023 | INR 26,667,000 | INR 25,867,000
PRJ009 | 01-02-2023 | INR 26,667,000 | INR 25,333,000
PRJ009 | 01-03-2023 | INR 26,667,000 | INR 25,600,000
PRJ009 | 01-04-2023 | INR 26,667,000 | INR 25,067,000
PRJ009 | 01-05-2023 | INR 26,667,000 | INR 25,333,000
PRJ009 | 01-06-2023 | INR 26,667,000 | INR 24,800,000
PRJ009 | 01-07-2023 | INR 26,667,000 | INR 25,600,000
PRJ009 | 01-08-2023 | INR 26,667,000 | INR 25,067,000
PRJ009 | 01-09-2023 | INR 26,667,000 | INR 25,333,000
PRJ009 | 01-10-2023 | INR 26,667,000 | INR 24,800,000
PRJ009 | 01-11-2023 | INR 26,667,000 | INR 25,067,000
PRJ009 | 01-12-2023 | INR 26,667,000 | INR 25,333,000
PRJ009 | 01-01-2024 | INR 26,667,000 | INR 25,067,000
PRJ009 | 01-02-2024 | INR 26,667,000 | INR 25,600,000
PRJ009 | 01-03-2024 | INR 26,667,000 | INR 25,067,000
PRJ010 | 01-07-2023 | INR 21,500,000 | INR 21,500,000
PRJ010 | 01-08-2023 | INR 21,500,000 | INR 21,715,000
PRJ010 | 01-09-2023 | INR 21,500,000 | INR 21,930,000
PRJ010 | 01-10-2023 | INR 21,500,000 | INR 21,500,000
PRJ010 | 01-11-2023 | INR 21,500,000 | INR 21,715,000
PRJ010 | 01-12-2023 | INR 21,500,000 | INR 21,715,000
PRJ010 | 01-01-2024 | INR 21,500,000 | INR 21,930,000
PRJ010 | 01-02-2024 | INR 21,500,000 | INR 21,500,000
PRJ010 | 01-03-2024 | INR 21,500,000 | INR 21,715,000
PRJ010 | 01-04-2024 | INR 21,500,000 | INR 21,715,000
PRJ010 | 01-05-2024 | INR 21,500,000 | INR 21,500,000
PRJ010 | 01-06-2024 | INR 21,500,000 | INR 21,715,000

## Raw_Project_Progress
PRJ_CODE | PROGRESS_MONTH | SCHEDULED_PCT | SITE_ACTUAL_PCT
PRJ001 | 01-01-2023 | 4.0% | 3.0%
PRJ001 | 01-02-2023 | 8.0% | 6.0%
PRJ001 | 01-03-2023 | 13.0% | 10.0%
PRJ001 | 01-04-2023 | 18.0% | 14.0%
PRJ001 | 01-05-2023 | 24.0% | 18.0%
PRJ001 | 01-06-2023 | 30.0% | 23.0%
PRJ001 | 01-07-2023 | 37.0% | 28.0%
PRJ001 | 01-08-2023 | 44.0% | 34.0%
PRJ001 | 01-09-2023 | 51.0% | 40.0%
PRJ001 | 01-10-2023 | 58.0% | 46.0%
PRJ001 | 01-11-2023 | 65.0% | 52.0%
PRJ001 | 01-12-2023 | 72.0% | 58.0%
PRJ001 | 01-01-2024 | 78.0% | 63.0%
PRJ001 | 01-02-2024 | 84.0% | 68.0%
PRJ001 | 01-03-2024 | 89.0% | 72.0%
PRJ001 | 01-04-2024 | 93.0% | 76.0%
PRJ001 | 01-05-2024 | 96.0% | 79.0%
PRJ001 | 01-06-2024 | 98.0% | 82.0%
PRJ002 | 01-03-2023 | 5.0% | 5.0%
PRJ002 | 01-04-2023 | 10.0% | 9.0%
PRJ002 | 01-05-2023 | 16.0% | 15.0%
PRJ002 | 01-06-2023 | 22.0% | 21.0%
PRJ002 | 01-07-2023 | 29.0% | 28.0%
PRJ002 | 01-08-2023 | 36.0% | 35.0%
PRJ002 | 01-09-2023 | 43.0% | 42.0%
PRJ002 | 01-10-2023 | 50.0% | 49.0%
PRJ002 | 01-11-2023 | 57.0% | 56.0%
PRJ002 | 01-12-2023 | 64.0% | 62.0%
PRJ002 | 01-01-2024 | 70.0% | 68.0%
PRJ002 | 01-02-2024 | 76.0% | 74.0%
PRJ002 | 01-03-2024 | 81.0% | 79.0%
PRJ002 | 01-04-2024 | 86.0% | 84.0%
PRJ002 | 01-05-2024 | 90.0% | 88.0%
PRJ002 | 01-06-2024 | 93.0% | 91.0%
PRJ003 | 01-01-2023 | 6.0% | 6.0%
PRJ003 | 01-02-2023 | 12.0% | 13.0%
PRJ003 | 01-03-2023 | 19.0% | 20.0%
PRJ003 | 01-04-2023 | 26.0% | 27.0%
PRJ003 | 01-05-2023 | 33.0% | 35.0%
PRJ003 | 01-06-2023 | 40.0% | 42.0%
PRJ003 | 01-07-2023 | 48.0% | 50.0%
PRJ003 | 01-08-2023 | 56.0% | 58.0%
PRJ003 | 01-09-2023 | 64.0% | 66.0%
PRJ003 | 01-10-2023 | 72.0% | 74.0%
PRJ003 | 01-11-2023 | 80.0% | 82.0%
PRJ003 | 01-12-2023 | 87.0% | 89.0%
PRJ003 | 01-01-2024 | 92.0% | 94.0%
PRJ003 | 01-02-2024 | 96.0% | 97.0%
PRJ003 | 01-03-2024 | 98.0% | 99.0%
PRJ003 | 01-04-2024 | 100.0% | 100.0%
PRJ004 | 01-04-2023 | 5.0% | 4.0%
PRJ004 | 01-05-2023 | 10.0% | 9.0%
PRJ004 | 01-06-2023 | 15.0% | 14.0%
PRJ004 | 01-07-2023 | 21.0% | 20.0%
PRJ004 | 01-08-2023 | 27.0% | 26.0%
PRJ004 | 01-09-2023 | 33.0% | 32.0%
PRJ004 | 01-10-2023 | 39.0% | 38.0%
PRJ004 | 01-11-2023 | 45.0% | 44.0%
PRJ004 | 01-12-2023 | 51.0% | 50.0%
PRJ004 | 01-01-2024 | 57.0% | 56.0%
PRJ004 | 01-02-2024 | 63.0% | 61.0%
PRJ004 | 01-03-2024 | 68.0% | 66.0%
PRJ004 | 01-04-2024 | 73.0% | 71.0%
PRJ004 | 01-05-2024 | 77.0% | 75.0%
PRJ004 | 01-06-2024 | 81.0% | 79.0%
PRJ005 | 01-02-2023 | 5.0% | 4.0%
PRJ005 | 01-03-2023 | 11.0% | 8.0%
PRJ005 | 01-04-2023 | 17.0% | 12.0%
PRJ005 | 01-05-2023 | 23.0% | 16.0%
PRJ005 | 01-06-2023 | 30.0% | 20.0%
PRJ005 | 01-07-2023 | 37.0% | 25.0%
PRJ005 | 01-08-2023 | 44.0% | 30.0%
PRJ005 | 01-09-2023 | 51.0% | 36.0%
PRJ005 | 01-10-2023 | 58.0% | 42.0%
PRJ005 | 01-11-2023 | 65.0% | 48.0%
PRJ005 | 01-12-2023 | 72.0% | 54.0%
PRJ005 | 01-01-2024 | 79.0% | 60.0%
PRJ005 | 01-02-2024 | 85.0% | 65.0%
PRJ005 | 01-03-2024 | 90.0% | 69.0%
PRJ005 | 01-04-2024 | 94.0% | 73.0%
PRJ005 | 01-05-2024 | 97.0% | 76.0%
PRJ005 | 01-06-2024 | 99.0% | 79.0%
PRJ006 | 01-05-2023 | 4.0% | 4.0%
PRJ006 | 01-06-2023 | 8.0% | 8.0%
PRJ006 | 01-07-2023 | 13.0% | 12.0%
PRJ006 | 01-08-2023 | 18.0% | 17.0%
PRJ006 | 01-09-2023 | 24.0% | 23.0%
PRJ006 | 01-10-2023 | 30.0% | 29.0%
PRJ006 | 01-11-2023 | 36.0% | 35.0%
PRJ006 | 01-12-2023 | 42.0% | 41.0%
PRJ006 | 01-01-2024 | 48.0% | 47.0%
PRJ006 | 01-02-2024 | 54.0% | 53.0%
PRJ006 | 01-03-2024 | 60.0% | 58.0%
PRJ006 | 01-04-2024 | 65.0% | 63.0%
PRJ006 | 01-05-2024 | 70.0% | 68.0%
PRJ006 | 01-06-2024 | 74.0% | 72.0%
PRJ007 | 01-02-2023 | 5.0% | 3.0%
PRJ007 | 01-03-2023 | 10.0% | 7.0%
PRJ007 | 01-04-2023 | 16.0% | 11.0%
PRJ007 | 01-05-2023 | 23.0% | 16.0%
PRJ007 | 01-06-2023 | 30.0% | 21.0%
PRJ007 | 01-07-2023 | 37.0% | 27.0%
PRJ007 | 01-08-2023 | 45.0% | 33.0%
PRJ007 | 01-09-2023 | 53.0% | 40.0%
PRJ007 | 01-10-2023 | 61.0% | 47.0%
PRJ007 | 01-11-2023 | 69.0% | 54.0%
PRJ007 | 01-12-2023 | 76.0% | 61.0%
PRJ007 | 01-01-2024 | 83.0% | 67.0%
PRJ007 | 01-02-2024 | 89.0% | 73.0%
PRJ007 | 01-03-2024 | 94.0% | 78.0%
PRJ007 | 01-04-2024 | 97.0% | 82.0%
PRJ007 | 01-05-2024 | 99.0% | 85.0%
PRJ007 | 01-06-2024 | 100.0% | 87.0%
PRJ008 | 01-06-2023 | 4.0% | 3.0%
PRJ008 | 01-07-2023 | 9.0% | 7.0%
PRJ008 | 01-08-2023 | 15.0% | 12.0%
PRJ008 | 01-09-2023 | 21.0% | 17.0%
PRJ008 | 01-10-2023 | 28.0% | 23.0%
PRJ008 | 01-11-2023 | 35.0% | 29.0%
PRJ008 | 01-12-2023 | 42.0% | 35.0%
PRJ008 | 01-01-2024 | 49.0% | 41.0%
PRJ008 | 01-02-2024 | 56.0% | 47.0%
PRJ008 | 01-03-2024 | 63.0% | 53.0%
PRJ008 | 01-04-2024 | 69.0% | 59.0%
PRJ008 | 01-05-2024 | 75.0% | 65.0%
PRJ008 | 01-06-2024 | 80.0% | 70.0%
PRJ009 | 01-01-2023 | 7.0% | 7.0%
PRJ009 | 01-02-2023 | 14.0% | 14.0%
PRJ009 | 01-03-2023 | 21.0% | 22.0%
PRJ009 | 01-04-2023 | 29.0% | 30.0%
PRJ009 | 01-05-2023 | 37.0% | 38.0%
PRJ009 | 01-06-2023 | 45.0% | 47.0%
PRJ009 | 01-07-2023 | 53.0% | 55.0%
PRJ009 | 01-08-2023 | 62.0% | 64.0%
PRJ009 | 01-09-2023 | 71.0% | 73.0%
PRJ009 | 01-10-2023 | 79.0% | 81.0%
PRJ009 | 01-11-2023 | 86.0% | 88.0%
PRJ009 | 01-12-2023 | 92.0% | 94.0%
PRJ009 | 01-01-2024 | 96.0% | 97.0%
PRJ009 | 01-02-2024 | 98.0% | 99.0%
PRJ009 | 01-03-2024 | 100.0% | 100.0%
PRJ010 | 01-07-2023 | 5.0% | 5.0%
PRJ010 | 01-08-2023 | 11.0% | 10.0%
PRJ010 | 01-09-2023 | 17.0% | 16.0%
PRJ010 | 01-10-2023 | 24.0% | 23.0%
PRJ010 | 01-11-2023 | 31.0% | 30.0%
PRJ010 | 01-12-2023 | 38.0% | 37.0%
PRJ010 | 01-01-2024 | 46.0% | 44.0%
PRJ010 | 01-02-2024 | 53.0% | 51.0%
PRJ010 | 01-03-2024 | 60.0% | 58.0%
PRJ010 | 01-04-2024 | 67.0% | 65.0%
PRJ010 | 01-05-2024 | 73.0% | 71.0%
PRJ010 | 01-06-2024 | 79.0% | 77.0%

## Raw_Milestones
STAGE_GATE_ID | PROJECT_REF | DELIVERABLE_TITLE | TARGET_DEADLINE | SIGN_OFF_DATE | MILESTONE_STATUS
MLS001 | PRJ001 | Site Clearance & Soil Investigation | 2023-03-31 | 2023-04-10 | COMPLETED
MLS002 | PRJ001 | Substructure & Foundation Piling | 2023-08-31 | 2023-09-20 | COMPLETED
MLS003 | PRJ001 | RCC Superstructure & Pier Casting | 2024-02-28 | 2024-05-15 | COMPLETED
MLS004 | PRJ001 | Viaduct Erection & Track Bed | 2024-05-31 | PENDING / INCOMPLETE | DELAYED
MLS005 | PRJ001 | Signaling, Traction & Trial Runs | 2024-11-30 | PENDING / INCOMPLETE | IN PROGRESS
MLS006 | PRJ002 | Site Clearance & Excavation | 2023-04-30 | 2023-04-25 | COMPLETED
MLS007 | PRJ002 | Basement Retaining Wall & Raft | 2023-08-31 | 2023-08-30 | COMPLETED
MLS008 | PRJ002 | Tower Core & Superstructure (L1-L15) | 2024-01-31 | 2024-02-05 | COMPLETED
MLS009 | PRJ002 | Glass Curtain Glazing & Facade | 2024-06-30 | PENDING / INCOMPLETE | IN PROGRESS
MLS010 | PRJ002 | High-Speed Elevators & Commissioning | 2024-10-31 | PENDING / INCOMPLETE | IN PROGRESS
MLS011 | PRJ003 | Coastal Survey & Environmental Clearance | 2023-02-28 | 2023-02-20 | COMPLETED
MLS012 | PRJ003 | Seawall Reinforcement & Earthwork | 2023-06-30 | 2023-06-25 | COMPLETED
MLS013 | PRJ003 | Paved Promenade & Cycling Tracks | 2023-11-30 | 2023-11-20 | COMPLETED
MLS014 | PRJ003 | Solar Illumination & Public Amenities | 2024-02-28 | 2024-02-22 | COMPLETED
MLS015 | PRJ003 | Landscaping & Public Opening Handover | 2024-04-30 | 2024-04-18 | COMPLETED
MLS016 | PRJ004 | Geotechnical Survey & Demolition | 2023-05-31 | 2023-05-28 | COMPLETED
MLS017 | PRJ004 | Deep Foundation & Diaphragm Wall | 2023-09-30 | 2023-10-05 | COMPLETED
MLS018 | PRJ004 | Pre-cast Concrete Framing (G+8) | 2024-03-31 | 2024-04-02 | COMPLETED
MLS019 | PRJ004 | IGBC Platinum HVAC & Solar Grid | 2024-08-31 | PENDING / INCOMPLETE | IN PROGRESS
MLS020 | PRJ004 | Interior Fitouts & Smart Building BMS | 2025-01-31 | PENDING / INCOMPLETE | IN PROGRESS
MLS021 | PRJ005 | Excavation & Water Table Dewatering | 2023-04-15 | 2023-05-10 | COMPLETED
MLS022 | PRJ005 | Multi-Level Basement Parking Slab | 2023-09-15 | 2023-10-30 | COMPLETED
MLS023 | PRJ005 | Anchor Store & Atrium Framing | 2024-01-31 | 2024-04-20 | COMPLETED
MLS024 | PRJ005 | Multiplex Acoustic Shell & Escalators | 2024-05-31 | PENDING / INCOMPLETE | DELAYED
MLS025 | PRJ005 | Retail Fitouts & Fire Safety NOC | 2024-09-30 | PENDING / INCOMPLETE | IN PROGRESS
MLS026 | PRJ006 | Master Plan Approval & Boundary Walls | 2023-06-30 | 2023-06-20 | COMPLETED
MLS027 | PRJ006 | Towers A & B Substructure Piling | 2023-11-30 | 2023-12-05 | COMPLETED
MLS028 | PRJ006 | Monolithic Mivan Shuttering (Floor 1-10) | 2024-04-30 | 2024-05-12 | COMPLETED
MLS029 | PRJ006 | Plumbing, Electrical Conduits & Flooring | 2024-10-31 | PENDING / INCOMPLETE | IN PROGRESS
MLS030 | PRJ006 | Clubhouse, Sewage Plant & Handover | 2025-05-31 | PENDING / INCOMPLETE | IN PROGRESS
MLS031 | PRJ007 | Industrial Land Leveling & Grading | 2023-03-31 | 2023-03-25 | COMPLETED
MLS032 | PRJ007 | Heavy Industrial Flooring & PEB Erection | 2023-07-31 | 2023-09-10 | COMPLETED
MLS033 | PRJ007 | Battery Pack Assembly Cleanrooms | 2023-12-31 | 2024-03-15 | COMPLETED
MLS034 | PRJ007 | Automated Conveyor & Robotic Cells | 2024-04-30 | PENDING / INCOMPLETE | DELAYED
MLS035 | PRJ007 | High-Tension Substation & Trial Run | 2024-08-31 | PENDING / INCOMPLETE | DELAYED
MLS036 | PRJ008 | Utility Diversion & Traffic Rerouting | 2023-07-31 | 2023-08-20 | COMPLETED
MLS037 | PRJ008 | Pile Foundations & Pier Caps (P1-P24) | 2023-12-31 | 2024-01-25 | COMPLETED
MLS038 | PRJ008 | Pre-stressed Concrete Girder Launching | 2024-05-31 | 2024-06-18 | COMPLETED
MLS039 | PRJ008 | Deck Slab Casting & Bituminous Wearing | 2024-10-31 | PENDING / INCOMPLETE | IN PROGRESS
MLS040 | PRJ008 | Crash Barriers, Streetlights & Signage | 2025-02-28 | PENDING / INCOMPLETE | IN PROGRESS
MLS041 | PRJ009 | CRZ Regulatory Clearances & Boundary | 2023-02-15 | 2023-02-10 | COMPLETED
MLS042 | PRJ009 | 24 Luxury Villa Foundation & Plinth | 2023-06-30 | 2023-06-25 | COMPLETED
MLS043 | PRJ009 | Villa Superstructure & Terraces | 2023-10-31 | 2023-10-28 | COMPLETED
MLS044 | PRJ009 | Italian Marble, Smart Automation & MEP | 2024-01-31 | 2024-01-20 | COMPLETED
MLS045 | PRJ009 | Private Pools, Landscaping & Key Handover | 2024-03-31 | 2024-03-25 | COMPLETED
MLS046 | PRJ010 | Topographical Survey & Industrial Approvals | 2023-08-31 | 2023-08-25 | COMPLETED
MLS047 | PRJ010 | Laser Screed Heavy-Duty Flooring | 2023-12-31 | 2024-01-10 | COMPLETED
MLS048 | PRJ010 | Pre-Engineered Steel Shed Erection | 2024-04-30 | 2024-05-08 | COMPLETED
MLS049 | PRJ010 | Dock Levelers & Automated Fire Hydrants | 2024-10-31 | PENDING / INCOMPLETE | IN PROGRESS
MLS050 | PRJ010 | Solar Rooftop (1 MW) & Logistics Handover | 2025-04-30 | PENDING / INCOMPLETE | IN PROGRESS